## Slide 1: MoneyWatch Project Plan
CStudio
1/14/2016

## Slide 2: Team Responsibilities
Caleb (Developer, Product Owner)
Stay diligent in finishing deliverables on time
Notify customer ASAP if unforeseen delays arise. Work with customer to refine schedule
Prepare sprint demo materials for each demo (as specified later)
Joanna (Customer)
Check progress with product owner at least once in-between each demo
Prepare sprint demo materials for each demo (as specified later)
Complete each of the tasks requested by the developer during/after each demo to give constructive feedback
Use the product as appropriate to generate constructive feedback

## Slide 3: Sprint Demo Materials
Developer Brings…
Demo ppt presentation with following included:
  Current sprint plan (show task completion state)
  Backlog
  Next sprint plan
  Updated schedule
Demo of current capabilities
A current release to give to the customer to try out
Requests for customer use of current release to generate feedback
Proposed sprint plan for next sprint (customer approval desired)
Customer Brings…
List of constructive feedback items
  Features that did not work as advertised
  Features that the customer STRONGLY DISLIKED
  Features that customer LOVED
  New possible features that the customer realized we HAVE TO HAVE
  Additional items that are not that strong (LOVE, HATE, HAVE TO HAVE), but would be helpful to note

## Slide 4
2016
2016
Today
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Today
Jan 14
Start FileWatch Web
Jan 27
Finish Responsive UI Class
Feb 9
FileWatch Web working
Feb 15
Sprint 1 Plan
Feb 19
All loose items in office filed
Feb 22
Sprint 1 Demo
Mar 16
Sprint 2 Demo
Apr 10
Sprint 3 Demo
May 1
Sprint 4 Demo
May 29
Sprint 5 Demo
Jun 26
Sprint 6 Demo
Jul 24
Sprint 7 Demo
Aug 10
Working MW package deliverable
Aug 15
27 days
Feb 19
Mar 16
0%
Sprint 1
25 days
Mar 17
Apr 10
Sprint 2
21 days
Apr 11
May 1
Sprint 3
28 days
May 2
May 29
Sprint 4
28 days
May 30
Jun 26
Sprint 5
28 days
Jun 27
Jul 24
Sprint 6
17 days
Jul 25
Aug 10
Sprint 7
5 days
Aug 11
Aug 15
Final Testing/Packaging